## Sheet1
Next Step
Schedule of SIP/AIP Preparation Activities
| Activities | December | January | February | March | April | May | June | July | August | September | October | November | December | January
1 | Seminar - Workshop on SBM Framework and Revisiting SIP and adjusting AIP
2 | Phase 1 | December: Dec. 9-10, 2012
3 | Phase 2 | March: Mar. 14-15, 2013
4 | *SWOT Accomplishment | bar: March to April
5 | Phase 3 | April: Apr. 11-12, 2013
6 | * School Preparation of SIP/AIP | bar: April
7 | * Submission of SIP/AIP Draft | bar: April
8 | Organization of Division SIP Evaluators | April: Apr. 24, 2013
9 | Submission of AIP 2013 | May: 1st week of May
| Submission of SIP 2014-2016/ AIP 2014 | June: 2013-06-10
10 | Evaluation of SIP 2014-2016/ AIP 2014 | July: July
11 | Approval of SIP/AIP by SDS | August: August
12
13
14
15
16
17
18